## Sheet1
Task | Duration | 26.9.19 | 9.10.19 | 6.11.19 | 29.11.19 | 14.12.19 | 19.12.19
ANALYSIS | 13 Days
Definition of project | 5 Days | 1
Definition of problems | 3 Days | 4
Solutions of problems | 2 Days | 6
Determining of Programming Languages | 1 Day | 7
Summary of the Analysis | 2 Days | 9
DESIGN | 28 Days
Determining of Working Platform | 1 Day |  | 10
Ordering the components | 7 Days |  | 17
Drawing wire schematics | 2 Days |  | 19
Finding Libraries | 1 Days |  | 20
Writing Algorithm of the System | 10 Days |  | 30
Interface Design | 4 Days |  | 4
Summary of the Design | 1 Day |  | 5
Making Presentation about design phase | 1 Day |  | 6
IMPLEMENTATION | 23 Days
Wiring Components | 3 Days |  |  | 9
Code implementation of Home Automation | 7 Days |  |  | 16
Interface Implementation of Home Automation | 5 Days |  |  | 21
Combining components, code and interface | 7 Days |  |  | 28
Making Presentation about implementation phase | 1 Day |  |  | 29
TESTING | 15 Days
Determining the tests | 5 Days |  |  |  | 4
Testing of the wiring | 1 Day |  |  |  | 5
Testing of the code | 5 Days |  |  |  | 10
Testing of the interface | 2 Days |  |  |  | 12
Making Presentation about testing phase | 2 Days |  |  |  | 14
MAINTENANCE | 5 Days
Optimize all codes | 4 Days |  |  |  |  | 18
Presentation of the project after maintenance | 1 Day |  |  |  |  | 19