## Sheet1
Task | Duration | 26.9.19 | 9.10.19 | 6.11.19 | 29.11.19 | 14.12.19 | 19.12.19
ANALYSIS | 13 Days
Definition of project | 5 Days
Definition of problems | 3 Days
Solutions of problems | 2 Days
Determining of Programming Languages | 1 Day
Summary of the Analysis | 2 Days
DESIGN | 28 Days
Determining of Working Platform | 1 Day
Ordering the components | 7 Days
Drawing wire schematics | 2 Days
Finding Libraries | 1 Days
Writing Algorithm of the System | 10 Days
Interface Design | 4 Days
Summary of the Design | 1 Day
Making Presentation about design phase | 1 Day
IMPLEMENTATION | 23 Days
Wiring Components | 3 Days
Code implementation of Home Automation | 7 Days
Interface Implementation of Home Automation | 5 Days
Combining components, code and interface | 7 Days
Making Presentation about implementation phase | 1 Day
TESTING | 15 Days
Determining the tests | 5 Days
Testing of the wiring | 1 Day
Testing of the code | 5 Days
Testing of the interface | 2 Days
Making Presentation about testing phase | 2 Days
MAINTENANCE | 5 Days
Optimize all codes | 4 Days
Presentation of the project after maintenance | 1 Day